## 📊 Dashboard
PrintLoop — User Stories Implementation Status
CATEGORY SUMMARY
Category | Total Stories | ✅ Done | ⚠️ Partial | ❌ Todo | % Done
Single Printing | 14 | 8 | 5 | 1
Group Printing | 7 | 0 | 1 | 6
Batch Printing | 1 | 0 | 1 | 0
Admin Panel | 15 | 0 | 7 | 8
TOTAL

## Single Printing
Single Printing — User Stories
Status | User Story | What's Implemented | Key Files | Gaps / Missing | Est. Hours | Owner | Done?
✅ Done | 1. Create account & sign in | Register, OTP verify, password reset all working | src/modules/customer/controllers/auth.controller.ts | ❌ Google OAuth not implemented |  |  | ☐ Open
✅ Done | 2. Upload document | Cloudinary presigned upload, multiple files supported | src/components/PrintFlow/UploadStep.tsx | ⚠️ No frontend file type validation |  |  | ☐ Open
✅ Done | 3. Configure print job | All settings with live price update | src/components/PrintFlow/PrintOptionsStep.tsx |  |  |  | ☐ Open
⚠️ Partial | 4. Review pricing | Price displayed clearly | src/components/PrintFlow/PrintSummary.tsx | 🔴 Pricing hardcoded (₦5/₦25). Needs pricingConfig table |  |  | ☐ Open
⚠️ Partial | 5. Select payment | Wallet + Paystack implemented | src/components/PrintFlow/PaymentStep.tsx | ❌ USSD not integrated. 🟠 No inline wallet top-up modal |  |  | ☐ Open
⚠️ Partial | 6. Payment confirmation | 6-char PIN shown, summary displayed | src/pages/PrintFlow.tsx step 4 | 🔴 QR code is placeholder SVG. ❌ No email receipt |  |  | ☐ Open
❌ Todo | 7. Choose kiosk | No kiosk finder exists | — | ❌ Needs map/list UI + GET /kiosks endpoint |  |  | ☐ Open
✅ Done | 8. Authenticate at kiosk | POST /printer/validate-code, 6-char PIN entry | PrintLoopKiosk.jsx, printer.service.ts | ⚠️ QR scanner not wired. 🔴 No API key auth |  |  | ☐ Open
✅ Done | 9. Confirm at kiosk | Preview screen shows all details | PrintLoopKiosk.jsx preview screen |  |  |  | ☐ Open
✅ Done | 10. Print & collect | start/complete endpoints working | printer.service.ts |  |  |  | ☐ Open
⚠️ Partial | 11. Handle errors | fail endpoint stores reason | printer.service.ts | ❌ No auto-requeue. 🟡 No partial-print resume |  |  | ☐ Open
⚠️ Partial | 12. Privacy & security | Cloudinary encryption in transit | fileUpload.service.ts | 🔴 No auto-delete. 🔴 No Helmet.js headers |  |  | ☐ Open
✅ Done | 13. View history | Print history page with all jobs | src/pages/PrintJobs.tsx | ❌ No receipt download |  |  | ☐ Open
⚠️ Partial | 14. Reuse easily | Login persists | — | ❌ No reprint feature. ❌ No active promos |  |  | ☐ Open

## Group Printing
Group Printing — User Stories
Status | User Story | What's Implemented | Key Files | Gaps / Missing | Est. Hours | Owner | Done?
❌ Todo | Story 1: Create group link | GroupSession entity exists | groupSession.entity.ts | ❌ No API endpoints. ❌ No CreateGroupSession.tsx |  |  | ☐ Open
❌ Todo | Story 2: Join & upload | No participant flow | — | ❌ join/upload endpoints not built. ❌ No /join/[id] route |  |  | ☐ Open
❌ Todo | Story 3: Watermark ID | watermarkId column exists | printJob.entity.ts | ❌ No watermarking worker. pdf-lib not installed |  |  | ☐ Open
❌ Todo | Story 4: Monitor & close | No host dashboard | — | ❌ GET /group-sessions/:id not built. ❌ No GroupDashboard.tsx |  |  | ☐ Open
❌ Todo | Story 5: Batch token | batchToken column exists | groupSession.entity.ts | ❌ close endpoint not built |  |  | ☐ Open
❌ Todo | Story 6: Print at kiosk | validate-code exists but no batch support | printer.service.ts | ❌ get-job must return files[] for batch tokens |  |  | ☐ Open
⚠️ Partial | Story 7: Security & audit | Encryption same as single print | auditLog.entity.ts | ⚠️ AuditLog missing columns. ❌ No access audit |  |  | ☐ Open

## Batch Printing
Batch Printing — User Stories
Status | User Story | What's Implemented | Key Files | Gaps / Missing | Est. Hours | Owner | Done?
⚠️ Partial | Personal batch | Backend supports PERSONAL_BATCH type | printJob.service.ts, BatchUploadStep.tsx | 🟡 No per-file settings UI. ❌ No partial resume |  |  | ☐ Open

## Admin Panel
Admin Panel — User Stories
Status | User Story | What's Implemented | Key Files | Gaps / Missing | Est. Hours | Owner | Done?
⚠️ Partial | Story 1: System overview | Service exists but only returns totalUsers | dashboard.service.ts | 🔴 Missing revenue/pages/kiosks stats. ❌ No admin UI |  |  | ☐ Open
❌ Todo | Story 2: Monitor fleet | Kiosk entity exists (needs creation) | kiosk.entity.ts | ❌ GET /admin/kiosks not built. ❌ No KioskManagement.tsx |  |  | ☐ Open
❌ Todo | Story 3: Control kiosk | No endpoints | — | ❌ PATCH /admin/kiosks/:id/status not built |  |  | ☐ Open
⚠️ Partial | Story 4: View jobs | Basic CRUD exists | admin/printJob.service.ts | ❌ No JobViewer.tsx |  |  | ☐ Open
❌ Todo | Story 5: Requeue jobs | failureReason stored | printJob.entity.ts | ❌ requeue endpoint not built |  |  | ☐ Open
❌ Todo | Story 6: Monitor groups | GroupSession entity exists | groupSession.entity.ts | ❌ No admin endpoints. ❌ No GroupSessionViewer.tsx |  |  | ☐ Open
❌ Todo | Story 7: Manage pricing | No entity or endpoints | — | 🔴 Create pricingConfig entity. ❌ pricing CRUD not built |  |  | ☐ Open
⚠️ Partial | Story 8: Promotions | Promotion entity exists | promotion.entity.ts | ❌ POST/PATCH /admin/promotions not built. ❌ No UI |  |  | ☐ Open
⚠️ Partial | Story 9: Transactions | Payment entity + basic lookup | admin/payment.service.ts | ❌ No admin transaction UI |  |  | ☐ Open
❌ Todo | Story 10: Refunds | No logic exists | — | ❌ refund endpoint not built. Needs Paystack API |  |  | ☐ Open
⚠️ Partial | Story 11: User accounts | Basic lookup exists | admin/user.service.ts | ❌ No block/unblock. ❌ No UI |  |  | ☐ Open
❌ Todo | Story 12: Reports | No endpoints | — | ❌ GET /admin/reports not built |  |  | ☐ Open
⚠️ Partial | Story 13: System settings | Max file size enforced in validation | fileUpload.validation.ts | ❌ No settings entity. ❌ No UI. 🔴 No auto-delete |  |  | ☐ Open
⚠️ Partial | Story 14: Roles & permissions | AdminRole entity exists | adminRole.entity.ts | ❌ Role CRUD not built. ❌ No RBAC middleware. ❌ No UI |  |  | ☐ Open
⚠️ Partial | Story 15: Audit log | AuditLog entity exists | auditLog.entity.ts | ⚠️ Missing columns. ❌ viewer endpoint not built. ❌ No UI |  |  | ☐ Open