## 📊 Dashboard
PrintLoop — Implementation Checklist & Status Dashboard
PHASE COMPLETION SCORECARD
Phase | Description | Status | Done | Partial | Todo | Total Tasks | % Complete | Est. Hours Remaining | Owner | Target Date | Notes
Phase 1 – Foundation | DB entities & schema | ✅ Done | 22 | 4 | 0 |  |  | 0 | Backend Dev | Completed
Phase 2 – Customer App | Single & batch print flow | ⚠️ Partial | 18 | 8 | 5 |  |  | 24 | Full Stack | May 2026
Phase 3 – Group Printing | Host/participant group flow | ❌ Todo | 3 | 0 | 22 |  |  | 120 | Full Stack | Jun 2026
Phase 4 – Kiosk API | Printer endpoints | ✅ Done | 14 | 5 | 0 |  |  | 8 | Backend Dev | Completed
Phase 5 – Admin Panel | Operations dashboard | ⚠️ Partial | 6 | 2 | 28 |  |  | 180 | Full Stack | Jul 2026
Phase 6 – Security | Tests, retention, audit | ❌ Todo | 0 | 0 | 20 |  |  | 80 | All Devs | Aug 2026
TOTALS
LEGEND |  |  |  |  | PRIORITY LEGEND
✅ Done | Task fully implemented and tested |  |  |  | P0 – Critical | Must fix before any release
⚠️ Partial | Task started but incomplete / has gaps |  |  |  | P1 – High | Should be done in current sprint
❌ Todo | Task not yet started |  |  |  | P2 – Medium | Next sprint or milestone
[5 empty] | P3 – Low | Nice to have / future

## Phase 1 – Foundation
Phase 1 — Core Foundation & Database
DB entities, schema, and data model ¦ Status: ✅ Mostly complete — 4 schema gaps remaining
Status | Task / Feature | Detail / Acceptance Criteria | Priority | Component / File | Est. Hours | Owner | Notes | Link / PR | Done?
✅ Entities — Fully implemented
✅ Done | groupSession.entity.ts | hostId, groupName, deadline, sharedSettings (json), status enum (OPEN/CLOSED), batchToken — all present and linked | P2 – Medium | src/database/entities/groupSession.entity.ts | 0 | Backend | Complete. No changes needed. |  | ☐ Open
✅ Done | printJob.entity.ts — jobType enum | JOB_TYPE enum (single / personal_batch / group_batch) added. groupSessionId FK. watermarkId column present. | P2 – Medium | src/database/entities/printJob.entity.ts | 0 | Backend | Complete. |  | ☐ Open
✅ Done | file.entity.ts — printJobId FK | One-to-many relationship from PrintJob → File implemented correctly | P2 – Medium | src/database/entities/file.entity.ts | 0 | Backend | Complete. |  | ☐ Open
✅ Done | adminRole.entity.ts | name + permissions (json array). AdminProfile optionally linked. Role-based structure in DB. | P2 – Medium | src/database/entities/adminRole.entity.ts | 0 | Backend | Complete. |  | ☐ Open
✅ Done | auditLog.entity.ts | userId, userType, action, ipAddress, timestamp — all present | P2 – Medium | src/database/entities/auditLog.entity.ts | 0 | Backend | Complete. |  | ☐ Open
✅ Done | promotion.entity.ts | FREE_PAGES / PERCENTAGE_DISCOUNT / FIXED_DISCOUNT rule types, startDate, endDate, isActive — all implemented | P2 – Medium | src/database/entities/promotion.entity.ts | 0 | Backend | Complete. |  | ☐ Open
⚠️ Gaps — Schema updates needed
⚠️ Partial | file.entity.ts — add participantId | Plan requires participantId (uuid, nullable) on File entity so group-session uploads are traceable to a specific participant. Currently missing. | P1 – High | src/database/entities/file.entity.ts | 1 | Backend | Add column + migration. Needed before Phase 3. |  | ☐ Open
⚠️ Partial | file.entity.ts — add perFilePrintConfig | Personal batch needs file-level print config overrides (json, nullable). Currently printConfig is only on PrintJob, not per-file. | P1 – High | src/database/entities/file.entity.ts | 1 | Backend | Add json column. Needed before Phase 2 per-file batch UI. |  | ☐ Open
⚠️ Partial | auditLog — add resourceType, resourceId, payload | Only logs userId + action. No resourceType (varchar), resourceId (uuid), or payload (json) — limits audit trail usefulness for admin panel. | P2 – Medium | src/database/entities/auditLog.entity.ts | 1 | Backend | Add 3 nullable columns + migration. |  | ☐ Open
⚠️ Partial | promotion.entity.ts — add promoCode and maxUsage | No promo code string (varchar, unique, nullable) for customer-facing coupon redemption. No maxUsage (int, nullable) cap to limit redemptions. | P2 – Medium | src/database/entities/promotion.entity.ts | 1 | Backend | Add 2 columns + migration. |  | ☐ Open
❌ Todo | pricingConfig entity (new) | Pricing is currently hardcoded in printJob.service.ts (₦5 B/W, ₦25 color). Needs a DB-backed pricingConfig table (paperSize, colorType, duplexMultiplier, pricePerPage) so shop owners can adjust without a redeploy. | P0 – Critical | src/database/entities/pricingConfig.entity.ts (new) | 3 | Backend | Blocks admin panel pricing settings and promotions. |  | ☐ Open
❌ Todo | kiosks entity (new) | No kiosks table. Needed to assign API keys, track online/offline status, lastSeenAt, and shopId per device. Currently printer endpoints are unauthenticated. | P0 – Critical | src/database/entities/kiosk.entity.ts (new) | 2 | Backend | Blocks kiosk API auth and admin kiosk management. |  | ☐ Open
Total estimated hours this phase

## Phase 2 – Customer App
Phase 2 — Customer App: Single & Batch Printing
Single print flow, batch upload, payment, and print code ¦ Status: ⚠️ ~85% done
Status | Task / Feature | Detail / Acceptance Criteria | Priority | Component / File | Est. Hours | Owner | Notes | Link / PR | Done?
✅ Done — Single print flow
✅ Done | 4-step print wizard (PrintFlow.tsx) | Upload → Options → Preview/Summary → Print Code flow fully wired. RTK Query integrated. | P2 – Medium | src/pages/PrintFlow.tsx | 0 | Frontend |  |  | ☐ Open
✅ Done | Dynamic price calculation | useCalculatePriceMutation calls POST /print-jobs/calculate-price on every option change. Reactive. | P2 – Medium | src/store/services/printJobsApi.ts | 0 | Frontend |  |  | ☐ Open
✅ Done | Cloudinary presigned upload | getPresignedUrl → direct Cloudinary POST → fileKey returned. resource_type: auto handles PDF detection. | P2 – Medium | src/modules/customer/services/fileUpload.service.ts | 0 | Backend |  |  | ☐ Open
✅ Done | Paystack payment integration | PaymentMethod radio in step 2. Paystack redirect handled. webhook.controller.ts receives confirmation. | P2 – Medium | src/modules/services/paystack.service.ts | 0 | Backend |  |  | ☐ Open
✅ Done | Print code display (step 4) | createdJobData.printJob.code rendered as 6-char PIN on confirmation screen. | P2 – Medium | src/pages/PrintFlow.tsx | 0 | Frontend |  |  | ☐ Open
✅ Done | Personal batch — backend | JOB_TYPE.PERSONAL_BATCH, files[] array, cost aggregation across files — all in printJob.service.ts | P2 – Medium | src/modules/customer/services/printJob.service.ts | 0 | Backend |  |  | ☐ Open
✅ Done | Wallet funding page | Wallet page + walletApi RTK slice + fundWallet via Paystack implemented | P2 – Medium | src/pages/Wallet.tsx | 0 | Full Stack |  |  | ☐ Open
✅ Done | Print history page (PrintJobs) | getUserPrintJobs, cancel, delete wired through RTK Query. Status badges working. | P2 – Medium | src/pages/PrintJobs.tsx | 0 | Frontend |  |  | ☐ Open
⚠️ Partial — Needs completion
⚠️ Partial | QR code generation on print code screen | Placeholder SVG exists in PrintFlow step 4. No actual QR generation library integrated. Customers cannot scan at kiosk. | P0 – Critical | src/pages/PrintFlow.tsx | 2 | Frontend | Install qrcode.react or react-qr-code. Also store QR base64 server-side on job creation for SMS/email receipts. |  | ☐ Open
⚠️ Partial | PreviewStep — actual PDF rendering | fileBase64 is passed as empty string. Component exists but document is not rendered inline before payment. Customers cannot verify their file. | P1 – High | src/components/PrintFlow/PreviewStep.tsx | 4 | Frontend | Integrate pdfjs-dist or react-pdf. Load from Cloudinary URL. Show page count + thumbnail. |  | ☐ Open
⚠️ Partial | Inline wallet top-up during checkout | Low-balance badge shown but no in-flow top-up modal. User must navigate away to /wallet, losing all form state. | P1 – High | src/components/PrintFlow/PaymentStep.tsx | 5 | Frontend | Build WalletTopupModal. Trigger from Low Balance badge. Preserve Redux form state across modal open/close. |  | ☐ Open
⚠️ Partial | Pricing — move hardcoded values to DB | calculatePrice() uses ₦5 B/W and ₦25 color hardcoded in service. Not read from Promotion or config table. Cannot be changed without redeploy. | P0 – Critical | src/modules/customer/services/printJob.service.ts | 3 | Backend | Create pricingConfig entity (see Phase 1 gap). Add GET /pricing/config endpoint. Customer app fetches on page load. |  | ☐ Open
⚠️ Partial | Per-file settings in batch UI | BatchUploadStep plan requires per-document settings. UI currently applies uniform config across all files. No file-level override UX. | P2 – Medium | src/components/PrintFlow/BatchUploadStep.tsx | 8 | Frontend | Add accordion per file with individual option overrides. Requires perFilePrintConfig column on File entity (Phase 1 gap). |  | ☐ Open
⚠️ Partial | Paystack webhook — idempotency guard | webhook.controller.ts exists but no idempotency key check. Duplicate events (Paystack retries) could mark a payment complete multiple times. | P1 – High | src/modules/customer/controllers/webhook.controller.ts | 3 | Backend | Store processed paymentReference in DB. Check before processing. Return 200 silently on duplicates. |  | ☐ Open
⚠️ Partial | Frontend file type validation | Backend validates extensions correctly. Frontend drop zone accepts any file. Should mirror allowed_formats from Cloudinary upload params. | P2 – Medium | src/components/PrintFlow/UploadStep.tsx | 2 | Frontend | Add accept prop to file input: .pdf,.docx,.doc,.jpg,.png. Show user-friendly error for unsupported types. |  | ☐ Open
❌ Todo — Not started
❌ Todo | Stripe payment integration | Payment service references Stripe in plan but only Paystack is implemented. Needed for international customers. | P3 – Low | src/modules/services/stripe.service.ts (new) | 8 | Backend | Implement same PaymentService interface as Paystack. Toggle via PAYMENT_PROVIDER env var. |  | ☐ Open
❌ Todo | Email receipt after payment | No email sent after successful payment. Customer should receive PDF or HTML receipt with print code and QR. | P1 – High | src/modules/services/email.service.ts | 4 | Backend | Use nodemailer or Resend. Trigger from Paystack webhook handler after marking job PAID. |  | ☐ Open
❌ Todo | Push notifications (mobile) | Notification entity exists but no push notification delivery implemented. FCM / Expo push not wired. | P2 – Medium | src/modules/services/notification.service.ts | 6 | Backend | Integrate Firebase Admin SDK. Trigger on: job PAID, job PRINTING, job COMPLETE. |  | ☐ Open
Total estimated hours this phase

## Phase 3 – Group Printing
Phase 3 — Customer App: Group Printing
Host/participant collaborative printing ¦ Status: ❌ 0% built — schema only
Status | Task / Feature | Detail / Acceptance Criteria | Priority | Component / File | Est. Hours | Owner | Notes | Link / PR | Done?
✅ Done — Schema ready
✅ Done | GroupSession entity | hostId, groupName, deadline, sharedSettings (json), batchToken, status (OPEN/CLOSED) — all in DB | P2 – Medium | src/database/entities/groupSession.entity.ts | 0 | Backend |  |  | ☐ Open
✅ Done | PrintJob.groupSessionId FK | Link from PrintJob to GroupSession defined in entity | P2 – Medium | src/database/entities/printJob.entity.ts | 0 | Backend |  |  | ☐ Open
✅ Done | PrintJob.watermarkId column | Column exists for participant watermark tracking | P2 – Medium | src/database/entities/printJob.entity.ts | 0 | Backend |  |  | ☐ Open
❌ Todo — Backend: Group session API
❌ Todo | POST /customer/group-sessions — create session | Host creates a group session with groupName, deadline (datetime), sharedSettings (paperSize, color, duplex). Returns sessionId + share link. | P0 – Critical | src/modules/customer/routes/groupSession.routes.ts (new) | 6 | Backend | Use nanoid for short share-link IDs. e.g. printloop.ng/join/A3xKp |  | ☐ Open
❌ Todo | POST /customer/group-sessions/:id/join — participant join | Validates session is OPEN and deadline not passed. Creates participant record. Returns upload token for participant. | P0 – Critical | src/modules/customer/services/groupSession.service.ts (new) | 4 | Backend |  |  | ☐ Open
❌ Todo | POST /customer/group-sessions/:id/upload — participant upload | Participant uploads file. System generates watermarkId, calculates individual cost, queues watermarking BullMQ job. | P0 – Critical | src/modules/customer/services/groupSession.service.ts (new) | 6 | Backend | Do NOT watermark inline — queue as BullMQ job to avoid blocking request. |  | ☐ Open
❌ Todo | GET /customer/group-sessions/:id — host dashboard data | Returns list of participants with: name, fileUploaded (bool), paymentStatus, fileURL, cost. Host uses this to monitor progress. | P1 – High | src/modules/customer/services/groupSession.service.ts (new) | 4 | Backend |  |  | ☐ Open
❌ Todo | POST /customer/group-sessions/:id/close — close & generate batch token | Host closes session. Backend aggregates all paid participant jobs. Generates single batchToken. Sets status = CLOSED. | P0 – Critical | src/modules/customer/services/groupSession.service.ts (new) | 5 | Backend | Should reject if any participant has unpaid jobs (or allow host to override). |  | ☐ Open
❌ Todo | Scheduled cron — auto-close expired sessions | BullMQ repeatable job (runs every 15 min) that queries OPEN sessions where deadline < now and auto-closes them. | P1 – High | src/modules/services/scheduler.service.ts (new) | 3 | Backend | Use BullMQ repeat jobs. Send notification to host when session auto-closes. |  | ☐ Open
❌ Todo — Backend: PDF watermarking
❌ Todo | PDF watermarking BullMQ worker | After participant uploads, queue a job that: fetches PDF from Cloudinary, stamps watermarkId + participant name using pdf-lib, re-uploads to Cloudinary. | P1 – High | src/workers/watermark.worker.ts (new) | 8 | Backend | Install pdf-lib. Watermark should be subtle (corner stamp, low opacity). Re-upload with same folder structure. |  | ☐ Open
❌ Todo — Frontend: Host view
❌ Todo | CreateGroupSession.tsx | Form to define group name, deadline (date-time picker), enforced settings (paperSize, color, duplex toggles). Generates and displays share link. | P1 – High | src/pages/CreateGroupSession.tsx (new) | 8 | Frontend |  |  | ☐ Open
❌ Todo | GroupDashboard.tsx — host monitor screen | Host can see: participant list, upload status, payment status per person. Real-time updates via WebSocket or polling. 'Close Group' button when ready. | P1 – High | src/pages/GroupDashboard.tsx (new) | 12 | Frontend | Use WebSocket (infrastructure already exists in kiosk agent). Real-time is important UX here. |  | ☐ Open
❌ Todo | Batch token display screen | After host closes group, display single batchToken QR + PIN. Same design as individual print code screen. Allow SMS share. | P1 – High | src/pages/GroupDashboard.tsx (new) | 4 | Frontend |  |  | ☐ Open
❌ Todo — Frontend: Participant view
❌ Todo | /join/[sessionId] dynamic route | Public route participants land on from host's share link. Shows group details, deadline countdown, and Upload button. | P1 – High | src/pages/JoinGroup.tsx (new) | 5 | Frontend | Must work without login. Participant identifies via email or phone. |  | ☐ Open
❌ Todo | ParticipantUpload.tsx — participant upload flow | Upload file, see enforced settings from host, see individual cost, pay. Generate watermarkId on success. Show confirmation. | P1 – High | src/pages/ParticipantUpload.tsx (new) | 10 | Frontend | Reuse PrintFlow upload + payment components where possible. Override settings based on host's sharedSettings. |  | ☐ Open
❌ Todo — Kiosk: Group token handling
❌ Todo | Kiosk validate-code — handle group batch tokens | Current validate-code only handles single-job tokens. Needs to recognise GROUP_BATCH tokens and return files[] array (all participant files) to kiosk. | P1 – High | src/modules/printer/services/printer.service.ts | 6 | Backend | Update get-job to return files[] with watermarked URLs when jobType === GROUP_BATCH. |  | ☐ Open
Total estimated hours this phase

## Phase 4 – Kiosk API
Phase 4 — Kiosk Integration API
All printer endpoints for physical kiosk ¦ Status: ✅ Complete — 4 security/feature gaps
Status | Task / Feature | Detail / Acceptance Criteria | Priority | Component / File | Est. Hours | Owner | Notes | Link / PR | Done?
✅ Done — All endpoints implemented
✅ Done | POST /printer/validate-code | Checks code exists, payment completed, job not already printed. Returns jobNumber. Zod validated. | P2 – Medium | src/modules/printer/controllers/printer.controller.ts | 0 | Backend |  |  | ☐ Open
✅ Done | POST /printer/get-job | Returns PrintJobDetails: fileURL, printConfiguration, customerInfo, cost, fileName. Full detail for kiosk to render preview. | P2 – Medium | src/modules/printer/services/printer.service.ts | 0 | Backend |  |  | ☐ Open
✅ Done | POST /printer/start | Marks job PROCESSING, records printerId + printerName, sets startedAt timestamp. | P2 – Medium | src/modules/printer/services/printer.service.ts | 0 | Backend |  |  | ☐ Open
✅ Done | POST /printer/complete | Marks job COMPLETED, records completedAt, cost, totalPages. Triggers cleanup queue. | P2 – Medium | src/modules/printer/services/printer.service.ts | 0 | Backend |  |  | ☐ Open
✅ Done | POST /printer/fail | Marks job FAILED with failureReason string. | P2 – Medium | src/modules/printer/services/printer.service.ts | 0 | Backend |  |  | ☐ Open
✅ Done | GET /printer/ready-jobs | Returns up to 50 PENDING paid jobs for kiosk polling. Filtered by printerLocation if provided. | P2 – Medium | src/modules/printer/controllers/printer.controller.ts | 0 | Backend |  |  | ☐ Open
✅ Done | GET /printer/status/:code | Lightweight status check — returns job status without full details. Used for kiosk polling. | P2 – Medium | src/modules/printer/controllers/printer.controller.ts | 0 | Backend |  |  | ☐ Open
✅ Done | Zod validation on all printer inputs | validateCodeSchema, startPrintJobSchema, completePrintJobSchema etc. all defined and enforced. | P2 – Medium | src/modules/printer/validations/printer.validation.ts | 0 | Backend |  |  | ☐ Open
⚠️ Gaps — Security & features
❌ Todo | Kiosk API key authentication middleware | All printer endpoints are currently public — any caller can validate codes or mark jobs complete. Each kiosk should authenticate with an API key stored in the kiosks table. | P0 – Critical | src/middleware/kioskAuth.middleware.ts (new) | 4 | Backend | Create kiosks table (Phase 1 gap). Generate API keys per device. Add X-Kiosk-Key header validation middleware on /printer/* routes. |  | ☐ Open
❌ Todo | Group batch token support in get-job | get-job only returns single fileURL. For GROUP_BATCH tokens, must return files[] array with all participant fileURLs (watermarked). | P1 – High | src/modules/printer/services/printer.service.ts | 5 | Backend |  |  | ☐ Open
❌ Todo | PATCH /printer/progress — incremental page status | Plan mentions partial resumption on hardware failure. Currently status is all-or-nothing. Add pagesCompleted counter so kiosk can resume a partial job. | P2 – Medium | src/modules/printer/routes/printer.routes.ts | 4 | Backend | Add pagesCompleted (int) column to PrintJob. Update via new endpoint. Kiosk sends progress every N pages. |  | ☐ Open
❌ Todo | Server-side QR code generation at job creation | Code is a 6-char PIN only. QR image should be generated (using qrcode npm) and stored/returned at job creation time so kiosk, email, and SMS all use same QR. | P1 – High | src/modules/customer/services/printJob.service.ts | 3 | Backend | Install qrcode npm. Store qrCodeUrl on PrintJob. Return in both customer API and printer get-job. |  | ☐ Open
❌ Todo | Kiosk heartbeat endpoint | No mechanism for kiosk to ping the API to show it's online. Admin panel needs to know which kiosks are active. | P2 – Medium | src/modules/printer/routes/printer.routes.ts | 2 | Backend | Add GET /printer/heartbeat. Updates kiosk.lastSeenAt. Admin panel reads this for online/offline status. |  | ☐ Open
Total estimated hours this phase

## Phase 5 – Admin Panel
Phase 5 — Admin Panel
Operations dashboard for PrintLoop staff ¦ Status: ⚠️ ~20% backend, 0% frontend
Status | Task / Feature | Detail / Acceptance Criteria | Priority | Component / File | Est. Hours | Owner | Notes | Link / PR | Done?
✅ Done — Backend scaffold
✅ Done | Admin module folder structure | controllers/, routes/, services/, repositories/ all exist under src/modules/admin/ | P3 – Low | src/modules/admin/ | 0 | Backend |  |  | ☐ Open
✅ Done | Admin auth endpoints | Login/logout for admin users. JWT issued on login. | P2 – Medium | src/modules/admin/routes/auth.routes.ts | 0 | Backend |  |  | ☐ Open
✅ Done | AdminRole + AdminProfile entities | Role-based structure in DB. AdminProfile linked to User with optional role FK. | P2 – Medium | src/database/entities/adminRole.entity.ts | 0 | Backend |  |  | ☐ Open
✅ Done | Admin printJob CRUD (basic) | Search/filter print jobs, basic status updates | P2 – Medium | src/modules/admin/services/printJob.service.ts | 0 | Backend |  |  | ☐ Open
⚠️ Partial — Backend: Thin services needing expansion
⚠️ Partial | AdminDashboardService — aggregate metrics | getDashboardStats() only returns totalUsers + recentUsers. Missing: totalRevenue, pagesPrinted, activeSessions, onlineKiosks, jobsByStatus, revenueByDay (last 30d). | P0 – Critical | src/modules/admin/services/dashboard.service.ts | 6 | Backend | Use a single aggregate SQL query (SUM, COUNT, GROUP BY date) rather than multiple service calls. Returns in <100ms. |  | ☐ Open
❌ Todo — Backend: Missing endpoints
❌ Todo | Kiosk management endpoints | No /admin/kiosks routes. Cannot list kiosks, view lastSeenAt, set maintenance mode, or force-restart via API. | P1 – High | src/modules/admin/routes/kiosk.routes.ts (new) | 5 | Backend | GET /admin/kiosks, PATCH /admin/kiosks/:id/status. Reads from kiosks table (Phase 1 gap). |  | ☐ Open
❌ Todo | Group session viewer endpoints | No /admin/group-sessions routes to inspect batch details and participant status. | P2 – Medium | src/modules/admin/routes/groupSession.routes.ts (new) | 4 | Backend | GET /admin/group-sessions, GET /admin/group-sessions/:id (with participants). |  | ☐ Open
❌ Todo | Pricing config CRUD endpoints | No admin routes to read/update base pricing per paperSize/colorType. Currently hardcoded in service. | P0 – Critical | src/modules/admin/routes/pricing.routes.ts (new) | 4 | Backend | GET /admin/pricing, PATCH /admin/pricing/:id. Requires pricingConfig entity (Phase 1 gap). |  | ☐ Open
❌ Todo | Promotions CRUD endpoints | Promotion entity exists but no admin routes to create/edit/deactivate promotions. | P1 – High | src/modules/admin/routes/promotion.routes.ts (new) | 5 | Backend | Full CRUD. Include GET /admin/promotions/active for customer app to fetch active promos. |  | ☐ Open
❌ Todo | AdminRoles CRUD endpoints | AdminRole entity exists but no routes to create roles, assign permissions, or assign roles to admins. | P1 – High | src/modules/admin/routes/role.routes.ts (new) | 5 | Backend | Protect all admin routes with RBAC middleware that checks role.permissions against the requested action. |  | ☐ Open
❌ Todo | AuditLog viewer endpoint | No GET /admin/audit-logs route — logs written but unreadable through the API. Admin panel cannot display them. | P2 – Medium | src/modules/admin/routes/auditLog.routes.ts (new) | 3 | Backend | Read-only. Support pagination + filter by userId, action, date range. |  | ☐ Open
❌ Todo | Refund endpoint | Plan mentions issuing refunds from admin panel. No refund endpoint exists. Needs Paystack refund API integration. | P1 – High | src/modules/admin/services/payment.service.ts | 5 | Backend | Call Paystack /refund API. Store refundId on Payment entity. Update payment.status to REFUNDED. |  | ☐ Open
❌ Todo | Requeue failed jobs endpoint | No way to requeue a FAILED job back to PENDING for retry. Admin needs this when hardware fails. | P1 – High | src/modules/admin/services/printJob.service.ts | 3 | Backend | PATCH /admin/print-jobs/:id/requeue. Reset status to PENDING, clear failureReason, reset printerId. |  | ☐ Open
❌ Todo — Frontend: Admin React app (entire app missing)
❌ Todo | Admin React app — project scaffold | No admin panel frontend exists at all. Create separate Vite + React project in /admin subfolder (or monorepo). Set up routing, auth guard, RTK Query. | P0 – Critical | /admin/ (new project) | 8 | Frontend | Share TypeScript types from API via shared/ package. Use same design system as customer app. |  | ☐ Open
❌ Todo | Overview.tsx — aggregate metrics dashboard | Cards: online kiosks, revenue today/week/month, pages printed, active sessions. Charts: revenue over 30 days, jobs by status donut. | P1 – High | /admin/src/pages/Overview.tsx (new) | 12 | Frontend |  |  | ☐ Open
❌ Todo | KioskManagement.tsx | Table of all kiosks: name, shopId, status (online/offline/maintenance), lastSeenAt, jobsToday. Toggle maintenance mode. View job queue per kiosk. | P1 – High | /admin/src/pages/KioskManagement.tsx (new) | 10 | Frontend |  |  | ☐ Open
❌ Todo | JobViewer.tsx | Search/filter jobs by code, status, date, customer email. Actions: requeue failed, issue refund, view file, cancel. Export to CSV. | P1 – High | /admin/src/pages/JobViewer.tsx (new) | 14 | Frontend |  |  | ☐ Open
❌ Todo | GroupSessionViewer.tsx | List group sessions with host, participant count, status, total cost. Drill in to see per-participant details. | P2 – Medium | /admin/src/pages/GroupSessionViewer.tsx (new) | 8 | Frontend |  |  | ☐ Open
❌ Todo | PricingConfig.tsx | Table of price per page by (colorType, paperSize). Inline editable. Live preview calculator showing cost for sample job. | P1 – High | /admin/src/pages/PricingConfig.tsx (new) | 8 | Frontend |  |  | ☐ Open
❌ Todo | Promotions.tsx | Create/edit/deactivate promotions. Show active promotions with usage count. Rule builder UI. | P2 – Medium | /admin/src/pages/Promotions.tsx (new) | 10 | Frontend |  |  | ☐ Open
❌ Todo | AdminRoles.tsx | Create roles with permission scope checkboxes. Assign roles to admin users. Show which admins have each role. | P2 – Medium | /admin/src/pages/AdminRoles.tsx (new) | 8 | Frontend |  |  | ☐ Open
❌ Todo | AuditLog.tsx | Read-only paginated log viewer. Filter by admin, action type, date range. Export to CSV for compliance. | P2 – Medium | /admin/src/pages/AuditLog.tsx (new) | 6 | Frontend |  |  | ☐ Open
Total estimated hours this phase

## Phase 6 – Security & Tests
Phase 6 — Privacy, Security & Testing
File retention, security hardening, automated tests ¦ Status: ❌ Not started
Status | Task / Feature | Detail / Acceptance Criteria | Priority | Component / File | Est. Hours | Owner | Notes | Link / PR | Done?
❌ Todo — File retention
❌ Todo | Auto-delete files 24h post-completion | BullMQ scheduled job (repeatable, every hour) that queries completed jobs older than 24h and calls cloudinary.uploader.destroy() on each fileURL, then nullifies fileURL in DB. | P0 – Critical | src/workers/fileCleanup.worker.ts (new) | 3 | Backend | Low effort, high privacy/cost impact. Add to BullMQ queue on job COMPLETE with 24h delay. |  | ☐ Open
❌ Todo | NDPR / GDPR data retention policy document | No documented policy on how long customer PII and file data is retained. Required for investor due diligence and compliance. | P1 – High | PRIVACY_POLICY.md + /admin settings | 2 | Legal / CTO | Files: 24h post-print. PII: anonymise after 12 months. Audit logs: retain 2 years. |  | ☐ Open
❌ Todo — Security hardening
❌ Todo | Helmet.js HTTP security headers | No Helmet or equivalent middleware. Missing X-Content-Type-Options, X-Frame-Options, HSTS, CSP headers. | P0 – Critical | src/app.ts | 1 | Backend | npm install helmet. app.use(helmet()). One line fix with significant security impact. |  | ☐ Open
❌ Todo | Rate limiting on sensitive endpoints | No rate limiting on /auth/login, /printer/validate-code, or any other endpoint. Open to abuse at scale. | P0 – Critical | src/middleware/rateLimit.middleware.ts (new) | 3 | Backend | npm install express-rate-limit redis. /auth/login: 5/min. /validate-code: 10/min. /printer/*: 100/min per kiosk key. Use Redis store. |  | ☐ Open
❌ Todo | Brute-force protection on print codes | Unlimited guesses on 6-char alphanumeric code. At 10 req/s that's ~50h to brute-force. Needs attempt tracking per IP. | P1 – High | src/modules/printer/services/printer.service.ts | 3 | Backend | After 5 wrong guesses on same IP within 10 minutes → 429. Use Redis counter with TTL. Log to auditLog. |  | ☐ Open
❌ Todo | Group session access control audit | No checks ensuring participant can only access their own session link. A participant from session A could potentially access session B data. | P1 – High | src/modules/customer/services/groupSession.service.ts (new) | 3 | Backend | Enforce sessionId + participantToken validation on every participant endpoint. Write tests covering cross-session access. |  | ☐ Open
❌ Todo | SQL injection / input sanitisation audit | Zod validation exists on most endpoints but a full audit of raw query usage and TypeORM query builder calls should be done. | P1 – High | All service files | 4 | Backend | Use TypeORM parameterised queries exclusively. Never concatenate user input into queries. |  | ☐ Open
❌ Todo — Testing
❌ Todo | Jest unit test setup (API) | No test files found in the API repository. No Jest config, no test utilities, no mocks. | P1 – High | src/**/*.spec.ts (new) | 6 | All Devs | Start with PrintJobService.createPrintJob() and PaymentService.createPaymentRequest(). Target >80% coverage on services. |  | ☐ Open
❌ Todo | Unit tests — PrintJobService | Test cases: createPrintJob (valid, invalid file, insufficient balance, duplicate code), calculatePrice (all colorType/duplex combinations), code generation uniqueness. | P1 – High | src/modules/customer/services/printJob.service.spec.ts (new) | 8 | Backend |  |  | ☐ Open
❌ Todo | Unit tests — PaymentService + Paystack webhook | Test cases: createPaymentRequest, handleWebhook (success, duplicate event, tampered signature), refund flow. | P1 – High | src/modules/services/payment.service.spec.ts (new) | 6 | Backend | Mock Paystack HTTP calls with nock or jest.mock. Test idempotency guard. |  | ☐ Open
❌ Todo | Unit tests — printer.service (kiosk flow) | Test cases: validateCode (valid, expired, already-printed, wrong code), complete, fail, progress. | P1 – High | src/modules/printer/services/printer.service.spec.ts (new) | 5 | Backend |  |  | ☐ Open
❌ Todo | E2E test — full payment and code flow | Playwright or Cypress test: register → upload file → configure → pay (Paystack test mode) → receive code → kiosk validate → complete. Full happy path. | P2 – Medium | e2e/printFlow.spec.ts (new) | 12 | Full Stack | Use Paystack test keys. Mock Cloudinary upload. Test both wallet and card payment paths. |  | ☐ Open
❌ Todo | Vitest unit tests — customer React app | No tests in customer app. Test critical components: PrintFlow wizard state, price calculator, upload validation. | P2 – Medium | src/**/*.test.tsx (new) | 8 | Frontend |  |  | ☐ Open
Total estimated hours this phase

## 💡 Backlog & Ideas
PrintLoop — Backlog, Improvements & Suggestions
Area | Suggestion | Why it matters | Effort | Impact | Phase | Status | Owner
Auth & Onboarding | Add Google OAuth login | Reduces signup friction significantly. Most Nigerian students have Google accounts | Low | High | Phase 2 | ❌ Todo | Frontend
UX | WhatsApp file upload integration | Let users send files to a PrintLoop WhatsApp number. Major UX unlock for non-app users. | Medium | Very High | Phase 2 | ❌ Todo | Backend
UX | SMS print code delivery | Send code via SMS (Termii / Africa's Talking) immediately after payment. Many users miss email. | Low | High | Phase 2 | ⚠️ Partial | Backend
Payments | USSD payment option | Add Paystack USSD so users without internet or cards can pay. Critical for broad Nigeria coverage. | Medium | High | Phase 2 | ❌ Todo | Backend
Kiosk | QR code scanner support | Add a QR scanner input on the kiosk (webcam or dedicated scanner) so customers can scan instead of typing code. | Low | High | Phase 4 | ❌ Todo | Kiosk Dev
Kiosk | Offline mode for kiosk | Cache last N jobs locally so kiosk can print even during internet outages. Sync when reconnected. | High | Medium | Phase 4 | ❌ Todo | Kiosk Dev
Business | Shop owner mobile app | Shop owners need a mobile view to monitor jobs, handle paper-out alerts, and see earnings. | High | High | Phase 5 | ❌ Todo | Mobile
Business | Referral / affiliate programme | Give customers a referral code. ₦20 wallet credit per successful signup. Viral growth mechanism. | Low | High | Phase 5 | ❌ Todo | Full Stack
Analytics | Customer print analytics | Show customer: total spent, pages printed, most common file type. Increases wallet top-up behaviour. | Medium | Medium | Phase 5 | ❌ Todo | Full Stack
DX | Monorepo setup (Turborepo/nx) | Customer app, admin app, and kiosk app share types and components. Monorepo would eliminate duplication. | Medium | Medium | Phase 1 | ❌ Todo | DevOps
DevOps | CI/CD pipeline (GitHub Actions) | No CI/CD detected. Auto-run tests and deploy on merge to main. Critical before any growth. | Low | Very High | Phase 6 | ❌ Todo | DevOps
DevOps | Docker Compose for local dev | Document and provide a docker-compose.yml for local MySQL + Redis + API. Reduces new dev onboarding time. | Low | Medium | Phase 1 | ❌ Todo | DevOps
Compliance | Print copyright notice | Display copyright reminder on upload screen: 'Only upload files you own or have permission to print.' | Very Low | High | Phase 2 | ❌ Todo | Frontend
Performance | Redis caching for pricing config | Cache pricingConfig in Redis (TTL 1hr). Pricing is read on every job creation — DB round-trip is wasteful. | Low | Medium | Phase 2 | ❌ Todo | Backend
Performance | CDN for Cloudinary delivery | Ensure Cloudinary delivery URLs use CDN (auto quality, f_auto format). Reduces kiosk download time. | Very Low | Medium | Phase 4 | ❌ Todo | Backend